## Sheet1
AAUW Texas Strategic Plan 2022-2024
Goals | Timeline | Responsible Officer(s) | Date Completed
EDUCATION AND TRAINING – Addressing the barriers and implicit biases that hinder advancement of women and girls.
GOAL A: Provide training in diversity and inclusion for the Texas State AAUW Board several times a year. | September 2022 - May 2023 | President and DEI Officer | So far, only one training at a board meeting
GOAL B: Provide training in diversity, equity, and inclusion across the state for our membership once a year online and for AAUW branches as a program. | September 2022-May 2023 | Diversity and Inclusion Officer District Reps
GOAL C: Monitor the state legislature for bills impacting the education and well-being of women and girls during the upcoming legislative session.
1. Legislative Lobbyist will provide legislative information about bills to Public Policy Committee and the membership | November 2022 – May 2023 | Public Policy District Reps | On-going through Public Policy Update (Constant Contact briefs on Sundays), How Tos on website, Bi-weekly meetings with lobbyist, Kate, Bill track report, etc. | 2023 Public Policy Updates.docx
2. Prioritize the legislative issues to follow provided by the Legislative Lobbyist based on survey results of AAUW TX | September 2022 – November 2022 | Public Policy President | COALITIONS AND COLLABORATIONS.docx
3. Form coalitions with like-minded organizations to increase the impact of AAUW Texas. | September 2022 – May 2023 | Public Policy President | Survey results completed and prioritized Sept. 2022
ECONOMIC SECURITY - Ensuring livelihoods for women.
GOAL A: Increasing the tools Texas women can use to improve their economic equity.
1. Post a link to AAUW Work Smart Online on the AAUW Texas websiste; request branches to provide the link on their website also | September 2022 – post link – May 2024 | Webmaster President District Reps
2. Provide information to AAUW Texas members on how to become a Volunteer Deputy Registrar | August 2022 – September 2022 | Branch Services Officer | Completed September 2022
3. Collect information about number of events (high schools, libraries, etc.) at which Texas AAUW members have volunteered to register voters | September 2022 -- November 2022 | Branch Services Officer | Completed September 2022/ article in UWT
GOAL B: Lessen the pay gap between men and women in Texas
1. Provide monthly posts on social media regarding the consequences of pay inequity, including college debt, how the pay gap increases over time, what it is like for each racial group, etc. | September 2022 – June 2024 | Facebook Manager | Sent out some national emails and made some posts.
2. Recognize the various Equal Pay Days by demonstrating the gaps in UWT articles and on Facebook | September 2022 – June 2024 | AAUW Texas Board members Facebook Manager | Black Pay Day was sent out in Sept. /Sent out emails and some posts.
3. Provide written and oral testimony on state legislation related to women’s economic security. | November 2022 – May 2023 | Public Policy President Programs Members | Public Policy Comm. following legislative bills and alerting the membership along with Kate our lobbyist.
LEADERSHIP – Women as Leaders
GOAL A: Honor the value of women's contribution to society
1. Post the incredible accomplishments of women in the past and the continuing successes of women in the present on Facebook | September 2022-May 2024 | Facebook Manager, Board | Many posts on Facebook
2. Post opportunities for women on Facebook | September 2022-May 2024 | Facebook Manager, Board
GOVERNANCE AND SUSTAINABILITY - Ensuring the strength, relevance, and viability of AAUW well into the future.
GOAL A: Increase membership in Legacy Circle by 10%.
1. Write Articles in UWT about ease of becoming a Legacy Circle member | October 2022 – May 2024 | VP for Funds
2. Recognize the Legacy Circle members in AAUW Texas | September 2022 – May 2024 | VP for Funds
GOAL B: Branch Services and Communication
1. Distribute the UWT every other month. | September 2022 – May 2024 | President Newsletter Editor | On schedule thus far
2. Provide Zoom and in person meetings with branches | September 2022 – May 2024 | District Representatives | On schedule thus far
3. Provide quarterly Zoom meetings with officers of branches in membership, funds, public policy, and programs | September 2022 – May 2024 | VP Membership VP Funds Public Policy Officer VP Programs | On schedule thus far and have added Finance Chair now meeting with membership as of this spring
4. Share programming ideas gained from branches across the state by writing articles for UWT and/or posting them on Facebook or the website | September 2022 – May 2024 | District Representatives VP Membership VP Funds VP Program Public Policy Officer
Note on D7: Mary M:
Note on A9: NASW League of Women Voters Texas Business Women of San Antonio LULAC African-American (AKA & Delta Sigma Theta) NOW Texas Texas Impact